## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Ravalika | 07.09.25 | Background noise interference in audio files reducing model performance | Research Phase | Ravalika | Major | Added spectral gating and bandpass filtering to remove ambient noise before transcription | 06.09.25 | Closed | Fix tested and verified by QA
2 | Rishika | 16.09.25 | Large audio files (>30min) causing memory overflow | Data Preprocessing | Rishika | Critical | Added audio chunking mechanism to process files in 5-minute segments with overlap | 15.09.25 | Closed | No further action required
3 | Inayat | 24.09.25 | Whisper model selection - balancing accuracy vs speed | Model Selection | Inayat | Major | Tested base/small/medium models, selected 'small' for optimal balance (WER: 8.2%, Speed: 2.1x realtime) | 23.09.25 | Closed | Improvement noticeable in transcription accuracy
4 | Akshith | 03.10.25 | Multilingual audio causing language detection errors | Pipeline Design | Akshith | Major | Implemented language detection pre-step using langdetect, passing detected language to Whisper | 02.10.25 | Closed | Client confirmed solution effectiveness
5 | Rajeev | 11.10.25 | Video audio extraction pipeline not handling all codecs | Pipeline Design | Rajeev | Critical | Integrated ffmpeg-python with automatic codec detection and conversion to WAV PCM format | 10.10.25 | Closed | Documentation updated
6 | Sravanthi | 22.10.25 | Transcription results lacking punctuation and formatting | Post-processing | Sravanthi | Minor | Enabled Whisper's punctuation model, added text formatting with proper sentence case | 21.10.25 | Closed | Ready for deployment
7 | Surya Vamsi | 28.09.25 | Real-time progress indication missing during long transcriptions | UX Issue | Surya Vamsi | Minor | Added progress callback and status messages to GUI ("Transcribing... Please wait") | 27.10.25 | Closed | Resolved as per requirement
8 | Shrinidhi | 04.11.25 | Python not recognized in Command Prompt after installation | Deployment | Shrinidhi | Major | Added Python to system PATH, verified using 'py' launcher command | 03.11.25 | Closed | Ready for deployment
9 | Janvi | 06.11.25 | ffmpeg not installed/configured for audio extraction | Deployment | Janvi | Major | Downloaded ffmpeg binaries, added to system PATH, verified installation | 05.11.25 | Closed | Deployment successful, issue resolved
10 | Pooja | 11.11.25 | No GPU acceleration - slow transcription on CPU-only system | Performance | Pooja | Major | Optimized PyTorch to use CPU efficiently, documented GPU setup for users with NVIDIA cards | 10.11.25 | Closed | Optimized for user hardware; performance improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others